## Example
Business Planning - Nobody's Life
Business Change | Month
| Begin state | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Target state
| Working prototype | 1: Beta testing, establish partnerships; 5: Launch, iteration to best version, create community forum, marketing; 13: Distributing/marketing, creating workshops around the topic | 60k Steam downloads
| Basic testing | [18 empty] | 15k active forum users
| No business | [18 empty] | 2nd Game dev start
Partnership network
KPIs | Downloads | 0 | 0 | 0 | 0 | 10 | 10 | 25 | 50 | 50 | 50 | 50 | 50 | 1000 | 2000 | 5000 | 10000 | 15000 | 25000 | 58295
| Active forum users | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 50 | 100 | 500 | 2000 | 5000 | 10000 | 15000 | 15000
Projects & Initiatives | Product 1 (Game) | 1: Beta testing; 3: Prep for launch; 5: Launch EA version; 6: Iterate on user feedback, quick updates; 11: Final version; 13: Distribution
| Product 2 (Forum) | 3: Create community forum; 7: Launch and use it for feedback; 13: Use for wide-ranging discussion
| Business | 1: Set up business & administration; 5: Improve workflows; 9: Obtain finance for marketing; 13: Coop with partners to create workshops and community, etc/
Resources
Marketing | Partner organizations | 5: Game being used in workshops; 10: Building larger network of partner organizations
| Online | 5: Launch; 6: low-cost social media marketing; 11: Big marketing push (social & stores) + discount
| Community | 6: Build community; 13: Maintain and grow community
| Free | 5: Steam algorithm; 9: Mouth-to-mouth marketing
Costs | Salary | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 180000
| Hardware | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 9000
| Research/Promotion | 333 | 333 | 334 | 1000 | 1000 | 1000 | 2000 | 2000 | 2000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 3333 | 3333 | 3334 | 50000
| Etc. (paid assets,…) | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 54000
Income | Sales | 0 | 0 | 0 | 0 | 125 | 125 | 400 | 650 | 650 | 650 | 650 | 650 | 13000 | 26000 | 65000 | 130000 | 195000 | 325000 | 757900
| Partnerships | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 67500
| Crowdfunding | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
| Asset Sales | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 9000
Profit/Loss |  | -10833 | -21666 | -32500 | -44000 | -55375 | -16750 | -28850 | -40700 | -52550 | -64900 | -77250 | -89600 | -89600 | -76600 | -24600 | 94067 | 277734 | 591400 | 591400
social media marketing is not the best/efficient/sustainable way
indiedevelopers have less return investments from social media marketing; more efficient for publishers with player base
use kickstarter less for money but more for getting the name out and gain visibility
create a coming soon page for steam, allows for features like streamer broadcasting
create content for steam page, trailers, screenshots, little but efficient texts
look for fitting smaller influencers on twitch to promote the game
social media marketing needs a very well-defined target group to efficiently reach out to fitting customers
marketing is a helping resource, as a indie game the key factor for success is the quality of the game not the marketing
visuals are the first impact, even before the story
the art-style is a chance to get a good first impression for the customers and to gain customer interest
the trailer should give a nice view into the game
consider early-access version and a free demo for people to try out the game and then decide if they want to join early-access
look for specialized press (e.g. mental health press, indie game press), sometimes instead of paying for articles provide exclusive content (e.g. exclusive trailer for article)
don't use discounts too early but rather use them to move focus back to the game after a time
use steam game festivals for gaining visibility
evaluate different platforms to sell the game (g2a, epic games, indie game focussed platforms) and don't stop on Steam
Building a strong community is very important for indie games, once the community forum/channel is created, it is important to be active and answer questions quickly
Translate the game into multiple languages to gain more traction in other countries